| Challenge Program on Water and Food | ANNUAL REPORT 1 April 2005 to 1 March 2006 |
| --- | --- |

1	PROJECT PROFILE  (this information will appear once only as a header sheet to your reports when they are electronic)

| PROJECT NO.: PN - 35 | PROJECT TITLE: Community-Based Fish Culture |
| --- | --- |
| LEAD CPWF THEME: Aquatic Ecosystems and Fisheries (Theme 3) | LEAD CPWF BENCHMARK BASIN(S): Indo-Gangetic Basin |
| SECONDARY CPWF THEME(S): Themes 4, 1 and Theme 5) | SECONDARY RIVER BASIN(S): Mekong, Yellow, Niger, Yantze River Basins |
| MANAGING CENTER: The WorldFish Center | PROJECT DURATION: 01 April 2005 to 31 March 2010 |

- LINKED QUARTERLY PROGRESS REPORT (MILESTONE PLAN) (this  section of the report should contain your milestone tables, embedded in an excel spreadsheet. One three monthly section per page. You are required to provide comments against your milestones in this report period)

Table 1 – 4 are the Milestone Plans for the first year of Project operations presented in quarterly basis.

CPWF-PN 35 is a five-year interdisciplinary action research with an overall aim of enhancing water productivity to improve and sustain the livelihoods of the poor. The main activities of the project are to be conducted in seasonal floodplain and irrigation areas of three CPWF benchmark river basins (Indus-Ganges, Mekong and Yellow River Basins) and two non-benchmark basins of Niger and Yantze.

The underlying assumption of the project is that seasonal waterbodies (over flooded crop fields) and canals/reservoirs in irrigation schemes can be communally managed by stakeholders under equitable and sustainable sharing arrangements.  The contributions of the Project in terms of technical and institutional research results – the outputs, outcomes, and impacts are to be based on fish-culture trials in these communally-managed waterbodies.

Flooding seasons in the included river basins, however, start in May-June and the fish-culture trials would start in May-June of 2006, and in the next three years of the project.

What this means is that the first year of project operations all activities are in preparation to the fish-culture trials in the floodplains and irrigation system during the rainy season.

So that activities for Year 1 of the projects consisted mainly of:

- Processing of agreements and arrangements (MOA between WorldFish and National Lead Institutions; participating NGOs, other government agencies);

- Organizational meetings and workshops to start-up the Project in the region and the six participating countries;

- Scoping and selection of Project sites;

- Gathering of baseline information for the selected sites;

- Preparation of methodologies for technical options and institutional arrangements in the fish-culture trials, and water productivity measurement.

- Organization of farmers-participants in the project.

All these activities are undertaken in the first year of the project (and up to May and June 2006) as enumerated in the quarterly Milestone Plans (Tables 1-4). In terms of first year accomplishment of the Project, all of these ‘preparatory activities’ have satisfactorily undertaken (discussed in detail in the Milestone Reports) except for India, where the processing of MOA between ICAR and WorldFish encountered an unexpected setbacks and delays.  It is expected, however, that once the MOA is signed the groundwork would proceed up to speed and fish-culture trials could still be conducted as scheduled in the rainy season.

It terms of outputs, outcomes and impacts, the Project has no substantive results yet to report.  Again, the fish-culture trials would run for at least 3 years, in which conclusive outputs, outcomes and impacts will be derived.  It is expected, however, that even after one fish-culture trial, preliminary results could be analyzed to warrant initial outputs of the Project.

As presented in the last table below on ‘Predicted Outputs of the CPWF Phase 1, PN-35 is expected to contribute on the:

  - Integrating multiple use of water;

    - Institutional mechanisms for integrating fish and crop production

    - Methodologies for integrating fish and crop production; and

  - Environment, water and agricultural policies that enhance water productivity.

| This Annual Report is linked to: | CPWF Quarterly Report Format-d06.xls (yet to be linked) |
| --- | --- |

3	SUMMARY OF ACHIEVEMENTS OVER THE PAST TWELVE MONTHS

As indicated above (Section 2), the achievements of the Projects listed here are not in terms technical outputs, outcomes, and impacts as described in ‘CPWF’s predicted outputs’, but rather achievements in preparation to the fish-culture trials and towards achieving those goals (outputs)

3 (a)	PROJECT OUTPUTS: Technical Elements

| 3.1 What are the project’s main technical achievements (listed as outputs) over the past year? |
| --- |
| Nature of project output/s | Details |
| Activity 1: Development of methodology for measuring water productivity at the landscape level |
|  | Bangladesh: Outline methodology produced by PhD candidate (Istiaque Hossain). Work will extend from household to basin scales. At farm/ community level, work will commence with an assessment of the significance of water availability/ quality issues to overall livelihood security. Once piloted – the methodology will be adapted and replicated in other countries. |
| Activity 2: Assessment of the current and potential contribution of aquatic resources |
|  | All countries: Component of baseline survey developed for implementation in action-research and control sites in 6 countries. Bangladesh: Outline methodology produced by PhD candidate (Istiaque Hossain) |
| Activity 3: Development of participatory diagnostic and stakeholder-involving diffusion approach for community based fish culture in shared water bodies |
|  | Cambodia, Vietnam, China: Field staff training in adaptive learning component of action-research methodology. |
| Activity 4: Design of technical options for integrating living aquatic resources in irrigation systems and seasonal flood plains |
| 4.1 Identification of landscapes and stakeholders | Cambodia, Vietnam, Bangladesh: Conditions range from a high degree of flood and irrigation control (Vietnam) to negligible control (Cambodia). Two potential sites have been identified in Takeo and Svay Rieng Mekong Delta Districts of Cambodia. In the Vietnamese Mekong Delta, four communities (in Dong Thap, An Giang and Can Tho Provinces) have been selected and farmer implementation groups identified by RIA2 partners. In Bangladesh, action-research will take place in four controlled sites in 4 districts (2 in the Ganges-Meghna Basin and 2 in the Meghna Basin). China In China our FFRC partner has signed contracts with local officials and Fisheries Extension departments to work with two pilot communities in Jiangsu and Yunan Provinces. |
| 4.2 Assessment of users needs | All countries: Needs analysis is incorporated in a baseline survey which will be randomly administered to at least 10% of households in intervention and control communities. This will complement needs analysis incorporated in PRA formats developed by our IFPRI partners. |
| 4.3 Designing location specific technical options | Cambodia, Vietnam, Bangladesh: Interventions will focus on fenced rice-fish production in flooded fields. China: Interventions will be based on flood-plain rice-fish production in Yunan Province and canal pen culture in Jiangsu. |
| Activity 5. Design of institutional options for integrating living aquatic resources in irrigation systems and seasonal floodplains |
|  | Cambodia, Vietnam, China: Training on building institutions for community-based aquaculture and PRA formats (developed by IFPRI) given to field staff of partner organisations. |
| Activity 6. Implementation of identified technical and institutional options in selected sites |
| 6.1 Testing of identified technical and institutional options | Year 2+ activity |
| 6.2 Monitoring and evaluation | Longitudinal monitoring survey formats in development. Outputs of pre-coded baseline and monitoring formats will be stored in a relational ACCESS database to facilitate inter-site and country comparisons. Field staff in Vietnam and China have received introductory training in its data |
| 6.3 Dissemination of validated technical and institutional options | Year 2+ activity |
| Activity 7. Capacity building of NARES for supporting the community based fish culture in shared water bodies |
|  | Training workshops held in Cambodia, Vietnam and China covering the following areas; design/ adaptation of rice-fish options, institutional capacity assessment/ strengthening, survey design/ enumeration and data management. |

3 (b)	CPWF OUTPUTS: relevance to CPWF thematic areas and basin priorities

| 3.3 How will the outputs identified above contribute to the CPWF output/s attached? |
| --- |
| CPWF Outputs | Project Contributions |
| All project activities and achievements in the past 12 months are contributing to four main themes of CPWF namely Theme 1, 3, 4 and 5 as summarized below. |
| THEME 1 (Crop water productivity improvement) |
| Integrating multiple uses of water (Need-based water supply) | Literature review conducted by PhD student |
| THEME 3 (Aquatic ecosystems and fisheries) |
| Institutional mechanisms for integrating fish and crop production (Policy Institutions and Governance) | Being developed by IFPRI partner |
| Methodologies for assessment of water production and fisheries (Improving water productivity of aquatic ecosystem) | Literature review conducted by PhD student |
| Strategies for management of reservoir fisheries (Improving water productivity of aquatic ecosystem) | Pen based stocking in tertiary irrigation canals being tested in Jiangsu Province China. No selection of storage reservoir sites in the first year. |
| Methodologies for integrating fish and crop production (Improving water productivity of aquatic ecosystem) | Pilot sites for flood plain rice fish integration selected in Bangladesh, Vietnam and China (Yunan) – methodologies developed in Bangladesh and N. Vietnam are being adapted for use in new sites |
| THEME 4 (Integrated basin water management systems) |
| Environmental water and agricultural policies that enhance water productivity (Global trade and macro-economic and sectoral policies) |  |
| 3.4 Are there other CPWF outputs that your project is contributing to? |
| CPWF Outputs | Project Contributions |

3 (c)	OUTCOMES AND IMPACT

| Before attempting this section access these web pages for an overview of the basis of how we approach outcomes and impact. They are from the IDRC web page on ‘Outcome Mapping’). http://web.idrc.ca/uploads/user-S/10960530301karaoke.swf http://web.idrc.ca/en/ev-64698-201-1-DO_TOPIC.html |
| --- |
| 3.5 What are the ‘outcomes’ of your research to date? | What outcomes have been generated by the outputs (as listed in 3.1) that your project has yielded to date? Please be basin specific. |
| Output (from 3.1) | Resultant outcomes |
| Activity 1 Development of methodology for measuring water productivity at the landscape level | Field activities are insufficiently advanced to produce significant outcome or detect impact on primary or secondary stakeholders. |
| Activity 2 Assessment of the current and potential contribution of aquatic resources | As above |
| Activity 3 Development of participatory diagnostic and stakeholder-involving diffusion approach for community based fish culture in shared water bodies | As above |
| Activity 4 Design of technical options for integrating living aquatic resources in irrigation systems and seasonal flood | As above |
| Activity 5 Design of institutional options for integrating living aquatic resources in irrigation systems and seasonal floodplains | As above |
| Activity 6 Implementation of identified technical and institutional options in selected sites | As above |
| Activity 7 Capacity building of NARES for supporting the community based fish culture in shared water bodies | Field staff in Vietnam and China trained and applying action-research / adaptive learning methodology |
| 3.6 Who has used these outcomes? Provide evidence to justify your answer. | . |
| Outcomes | Intended/unintended users and their involvement/uptake in individual basins. |
| 3.7 Beyond what you have told us so far, what dissemination /information -sharing activities are you undertaking? |  |
| 3.8 How would you describe your projects contribution so far to the CPWF mandate of producing international public goods? |
| Type of international public goods | Status |
| Methodology | Commencing development of project web page |
| Publications | NA |

3 (d) TECHNICAL AND/OR MANAGEMENT ISSUES

| 3.9. Any problems or constraints - deviations - in the past year? | Local institutional constraints have delayed the signing of project MoU’s with partners in Mali and India (the issue is still being resolved in India). This has delayed project start up in these countries. At World Fish - delayed recruitment and staff changes have slowed start-up activity in country |
| --- | --- |
| 3.10 Any adjustments you would like to make in the coming year to make the project more efficient and effective? | Limit action-research interventions to pilot sites while focusing on capacity building of field staff and gaining greater contextual understanding to fine tune site-specific technology adaptation. Source additional funding for additional external PhD students – to conduct comparative analyses of strategic country combinations and support capacity building of local staff. |
| 3.11 Comment on your interactions with Theme Leaders | Theme 1 Leader: Theme 3 Leader: Theme 4 Leader: Theme 5Leader: |
| 3.12 Comment on your interaction with basin coordinators. | On Indo-Gangetic Basin. Little interaction as yet Mekong River Basin. Received useful advice on site selection in Cambodia |
| 3.13 Comment on your interactions with other CPWF and non-CPWF projects in the basin. | Good interaction with CP 10 sharing contextual information on project sites in Vietnam Mekong Delta |

4	CAPACITY BUILDING

| Category | Basin location | Activities and expected outcomes |
| --- | --- | --- |
| Masters students | Indo-Gangetic Basin |  |
| PhDs | Indo-Gangetic Basin | One PhD selected to focus on Activities 1 and 2 in Bangladesh. Project will support travel and field expenses. National University of Malaysia One PhD student selected to focus on institutional issues in Bangladesh. Bangladesh Agricultural University |
| NARES |  |  |
| Future needs | Indo-Gangetic and Mekon Basins | External PhD students to support local capacity building / training of NARES field staff and to conduct comparative analyses between different countries and basins |
|  | Indo-Gangetic | Local World Fish staff member will be recruited support and co-ordinate activities of PhD students in Bangladesh. |

5 	PROJECT PROCEDURES FOR DATA COLLECTION/STORAGE AND SHARING

| (a) Technical elements |
| --- |
| 5.1. Data collected: what is the extent of your data collection to date? | PRA and Baseline survey materials developed and being piloted in Bangladesh, Vietnam, Cambodia and China. Collection of baseline data has commenced in Vietnam. Relational ACCESS data based is being developed for management of baseline and follow-up longitudinal monitoring surveys in all action-research and control communities in 6 countries. |
| 5.2 Can any of this information be usefully shared now? | Non as yet. However training will be given to local staff in use of the relational database described above. This will incorporate data entry validation steps, facilitate inter-community and country comparisons and general increase the value of data collected through improved manageability and access. |
| 5.3 Data analysed: what is the extent of your data analysis to date? | NA |
| 5.4 Information shared: what knowledge or information have you shared to date and who with? | NA |
| (b) Project Management element: |
| 5.6. What notable management and implementation lessons have you learned to date, and what would you do differently as a result? | Further support is required to enable local partners to successfully support a consensual model of institutional capacity building in action-research sites. This is primarily being addressed through attempts to recruit additional PhD students with a core focus on this theme. |

6  WRITTEN MATERIALS

| Type/title | Related to which Output | Expected Date of Publication | Name of journal or main user of materials | Author/s |
| --- | --- | --- | --- | --- |
| PAPERS |
| Papers for national seminar/conference / workshop |  |  |  |  |
| Papers for international seminar/ conference /workshop See list of papers in Appendix 1 |  |  |  |  |
| PowerPoint Presentations PPT are available for all the presentations above |  |  |  |  |
| PUBLICATIONS |
| Journal Article: |  |  |  |  |
| Working Paper: |  |  |  |  |
| Research Paper |  |  |  |  |
| Policy paper / brief: |  |  |  |  |
| Book/Monograph: Environment and Livelihoods in Coastal Zones: Managing Agriculture-Fishery-Aquaculture |  |  |  |  |
| Chapters in books/proceedings: See list of chapters in books/proceedings in Appendix 1 |  |  |  |  |
| Other: |  |  |  |  |
| TRAINING MATERIALS |
| Course materials: |  |  |  |  |
| Other: |  |  |  |  |
| SURVEY MATERIALS |
| Survey proforma: |  |  |  |  |
| Analysis proforma: |  |  |  |  |
| PROJECT INFORMATION MATERIALS |
| Web site: |  |  |  |  |
| Posters: |  |  |  |  |
| Brochures: |  |  |  |  |
| Newsletters: |  |  |  |  |
| Other: |  |  |  |  |
| ANY OTHER WRITTEN MATERIALS THAT DO NOT FALL UNDER THE ABOVE CATEGORIES |

7	COMMUNICATIONS ACTIVITIES

| Type | Where held | When held | Who aimed at | Outcome |
| --- | --- | --- | --- | --- |
| PROJECT MANAGEMENT MEETINGS |
| NATIONAL SEMINARS / CONFERENCES / WORKSHOPS |
| Inception workshop (2 days) | Cambodia (Phnom Penh) | Jan 06 | Local PI’s, NGO, Commune leaders | Project rationale introduced. Further assessment of research sits required |
| Inception / training workshop (2 days) | Vietnam (Ho Chi Minh City) | Jan 06 | Local PI’s, Field staff, Commune leaders | Research sites and interventions agreed. Staff trained on survey implementation and data management |
| Inception / training workshop (2 days) | China (Wuxi) | Feb 06 | Local PI’s, Field Staff, Commune leaders | Research sites and interventions agreed. Staff trained on survey implementation and data management |
| Inception meeting (1 day) | Bangladesh (Dhaka) | Feb 06 | Local PI’s | Research sites and interventions agreed. PhD candidate selected. Budget agreed. Local WF support staff member identified. |
| REGIONAL SEMINARS / CONFERENCES / WORKSHOP S |
| INTERNATIONAL SEMINARS / CONFERENCES / WORKSHOP S |
| FARMER GROUP MEETINGS / WORKSHOPS / TRAINING SESSIONS / DEMONSTRATIONS |
| FIELD VISITS TO PROJECT PARTNERS |
| OTHER KEY COMMUNICATIONS ACTIVITIES |
| VIDEOS / DVD’s / PLAYS / SONGS / ORAL MATERIALS PRODUCED / RADIO PRESENTATIONS / TELEVISION |

What other communications activities did you undertake to keep in contact with your stakeholders over the year? Please note also any plans for the future, and any constraints to communicating as much as your would wish (other than financial resources for international and regional travel - that is a given) The farming community that you are working with? Policy makers, other decision makers and users of research that your project is aimed at?: The establishment of National Advisory Committee in Bangladesh. Members are Head of relevant Departments, aiming at having feedbacks on project findings, seeking at possibilities for up-taking research findings in development projects, and large scale dissemination of research findings Your partners? Others – including the general public? We have discussed with a group of scientists from IWMI, University of Hawaii, FAO, IRD…on the possibility of organizing an international conference on “Inland coastal management of tropical Delta”; March 2007 to mark the end of the project. What, if anything, do you think the CPWF (as a community) could do to reach a wider audience of scientists, policy makers, development agencies, extension workers, farming communities (others?) to increase the flow of information of your research results to users, or to increase the two way flow of information with your peers and users of your research? (this is not a compulsory question to answer but we want to get your views on how better to get the results of your research out and how better to link with your users without discriminating against any groups.)

8	INTELLECTUAL PROPERTY ISSUES

Not applicable

9	HIGHLIGHTS OF YOUR WORK THIS YEAR

1. What elements of your work this year do you want to highlight for inclusion in scientific reports that are produced by the CPWF (particularly the synthesis reports that capture your work from perspectives of the new understanding you are contributing to research, the impact for the basins which you work in, and the implications for other basins.) 2. Other than the research being undertaken, are there any project management techniques – including partnerships that would not otherwise have happened, influence on the priority setting process within your institute, closer contact with a farming community, a different way of interacting with end users, access and management of funds, that you have used as a result of being contracted under the CPWF that would not have been possible under other programs? Positive / negative.

10	STATUS OF EXPENDITURES AND RECEIPTS TO DATE (US$)

10 (a) Expenditures

You are required to report expenditures against your summary budget. Please edit the spreadsheet below by adding your total agreed budget and allocating the funds received to date (see question 9 (b)) against the appropriate line item.

|  |  |  |  | COST IN DOLLARS |
| --- | --- | --- | --- | --- |
| Pro | Budget Item Code | TOTAL BUDGET | EXPENDITURES TO DATE | BALANCE AVAILABLE |
|  | CONTRBIBUTED FUNDS |  |  |  |
|  | 1 | MATCHING FUNDS | 295000 |  | 295000 |
|  | RESOURCES REQUESTED FROM THE CHALLENGE PROGRAM ON WATER AND FOOD |
|  | 2 | PERSONNEL RENUMERATIONS, TRAVEL AND ACCOMODATION |
|  | 2.1 |  | PERSONNEL COSTS |  |  |  |
|  | 2.1.1 |  | Project Leader | 150000 | 60030 | 89970 |
|  | 2.1.2 |  | Principle investigators (International) | 255000 |  | 255000 |
|  | 2.1.3 |  | Principle investigators (National) | 55000 |  | 55000 |
|  | 2.1.4 |  | Consultants | 217000 | 40891 | 217000 |
|  | 2.1.5 |  | Support staff | 223200 |  | 223200 |
|  | 2.2 |  | TRAVEL AND ACCOMODATION |  |  |  |
|  | 2.2.1 |  | Project Leader | 20000 |  | 20000 |
|  | 2.2.2 |  | Principle investigators (International) | 70000 | 4779 | 29109 |
|  | 2.2.3 |  | Principle investigators (National) |  |  |  |
|  | 2.2.4 |  | Consultants & Support staff | 46072 |  | 46072 |
|  | 2.2.5 |  | Other project participants |  |  |  |
|  | 3 | RESEARCH OPERATIONAL COSTS |  |  |  |
|  | 3.1 |  | EQUIPMENTS |  |  |  |
|  | 3.1.1 |  | Office equipment | 28600 |  | 28600 |
|  | 3.1.2 |  | Laboratory equipment |  |  |  |
|  | 3.1.3 |  | Field equipment |  |  |  |
|  | 3.1.4 |  | Other equipment |  |  |  |
|  | 3.2 |  | COMMUNICATION COSTS AND CONSUMABLES |  |
|  | 3.2.1 |  | Communication expenses | 22000 |  | 22000 |
|  | 3.2.2 |  | Office supplies | 13300 | 1704 | 11596 |
|  | 3.2.3 |  | Laboratory supplies |  |  |  |
|  | 3.2.4 |  | Field research supplies | 289078 |  | 289078 |
|  | 3.2.5 |  | Other services (please specify) | 163000 | 33726 | 129274 |
|  |  | Total of 2 and 3 | 1552250 | 141130 | 1415899 |
|  | 4 | MISCELLANEOUS |  |  |  |
|  | 4.1 |  | CONTIGENCY (30%) | 46568 |  | 46568 |
|  | 4.2 |  | OVERHEADS | 73737 | 8854 | 64883 |
|  | 4.3 |  | Others (please specify) | 25355 | 1678 | 23677 |
|  |  | TOTAL REQUESTED FROM THE CPWF | 1697910 | 151662 | 1546248 |
|  | GRAND TOTAL | 1992910 |  |  |

10 (b) Receipts

| 1 | Total project budget (a) | 1697910 |  |
| --- | --- | --- | --- |
| 2 | 1st tranche payment received |  | 61077 |
|  | 2nd tranche payment received |  | 91616 |
|  | 3rd tranche payment received |  | 152692 |
|  | 4th tranche payment received |  |  |
| 3 | Total funds received to date (b) | 305385 |  |
| 4 | Balance of budget remaining (a – b) | 1392525 |  |

10 (c) Matching Funds

| Name of Institute | Type of support | Is this as agreed, or are there deviations | Risk to project in the case of deviations |
| --- | --- | --- | --- |
| Bangladesh |  | As agreed | None |
| Cambodia |  |  | None |
| Vietnam: |  |  |  |
| China |  |  |  |
| Mali |  |  |  |
| WorldFish |  | As agreed | None |

10 (d) General Overview

| Comment on expenditure compared with project progress - is it on track? | On track |
| --- | --- |
| Comment on time spent compared with project progress - is it on track? | Expenditure slower than planned due to delayed field activity |

11.  CPWF ASSESSMENTS *

| Assessment * | Basin Coordinator | Theme Leader | Managing Center Administrator | Consolidated assessment |
| --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | X | 1 | 2 | 3 | X | 1 | 2 | 3 | X |  |  |
| Is the Project contributing quality outputs towards Basin and Theme priorities? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Have you verified the progress and dissemination reported? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is the Project working according to its plan? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is the project sufficiently focused on CPWF objectives? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Does the project demonstrate a new research approach in the spirit of CPWF? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are provisions for stakeholder and end user involvement adequate? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are provisions for addressing gender issues adequate? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Are provisions for addressing environmental issues adequate? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| It is important that you provide feedback to the project leader on any actions suggested to resolve any inadequate assessments as well as observations and comments regarding progress to date and any technical, management or dissemination issues that you would like to provide. These should be provided to the project leader by the Managing Center. A separate page is provided for you to provide these comments. |

* Assessment: (1) Good: a high standard of work; (2) Adequate: an acceptable standard of work, but improvements are possible; (3) Inadequate: this aspect of the project is not up to standard and must be improved; (X) Not known.

RECOMMENDATION TO CPWF SECRETARIAT:	SATISFACTORY  /  UNSATISFACTORY  /  TERMINATE

Is there a need to change the plan of the project.  If so, why and how?

Comments to Secretariat from Managing Center to support this recommendation  (optional):

Feedback Comments from the Theme Leader to be provided to the Project Leader by the Managing Center

Feedback Comments from the Basin Coordinator to be provided to the Project Leader by the Managing Center

Note: the space available here for comments is not meant to be restrictive – use as much space as necessary

# Footnotes

This may not be applicable in all cases (i.e. for ‘grey’ publications such as a survey sheet)